## SCENARIOS
S:NO | Scenario ID | SCENARIOS
1 | SC_01 | Verification of Customer Amendments.
2 | SC_02 | Verification of Account Amendments.
3 | SC_03 | Verification of Deposits Amendments.
4 | SC_04 | Verification of Loan Amendments.
5 | SC_05 | Amendment Report verification
6 | SC_06 | Drop Down verification
7 | SC_07 | Menu verification
8 | SC_08 | Activity dropdown verification in customer amendments
9 | SC_09 | Activity dropdown verification in accountamendments

## TC_AUDIT REPORT
SCENARIO ID | SCENARIO | TEST CASE ID | TEST CASE | PRE REQUISITES | TEST DATA | STEPS | TEST STEPS | EXPECTED RESULT | ACTUAL RESULT | STATUS
Audit Report Phase 2 _UAT_SC_001 | Verification of Customer Amendments. | Audit Report Phase 2_UAT_SC_001_TC_001 | Verify that the Modified Customer name is reflecting in the client over view page(T24) | Individual Customer |  | 1 | Login to T24. | User should be able to login T24 application Successfully . | As Expected | INPROGRESS
[6 empty] | 2 | Navigate to the customer profile | Customer profile should be displayed.
[6 empty] | 3 | Edit name, Validate and commit the deal | Successfully commit the deal.
[6 empty] | 4 | Check the audit and verify the date and time in the audit tab. | Date and time should be in the correct format
|  | Audit Report Phase 2_UAT_SC_001_TC_002 | Verify that the user is able to validate the audit report for the Changed / Modified Customer name field without any selection criteria. |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully . | As Expected | INPROGRESS
[6 empty] | 2 | Click on Customer Audit Report from General Enquiries/Reports | User should be able to click on the menu
[6 empty] | 3 | Click on find Button. | user should be able to see all the customers who have changed the name
[6 empty] | 4 | Verify the Changed / Modified Customer name field in the report. | Changed / Modified Customer name field should be available in the report.
|  | Audit Report Phase 2_UAT_SC_001_TC_003 | Verify that the user is able to validate the audit report for the Changed / Modified Customer name field with Customer Number selection criteria. |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully . | As Expected | INPROGRESS
[6 empty] | 2 | Click on Customer Audit Report from General Enquiries/Reports | User should be able to click on the menu
[6 empty] | 3 | Enter the customer Number and click on Find button. | Report should get loaded successfully with Modified/Changed customer name.
|  | Audit Report Phase 2_UAT_SC_001_TC_004 | Verify that the modified/changed Phone Number (SMS) is reflecting in the client over view page(T24) |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Navigate to the customer profile | Customer profile should be displayed.
[6 empty] | 3 | Edit Phone Number, Validate and commit the deal | Successfully commit the deal.
[6 empty] | 4 | Check the audit and verify the date and time in the audit tab. | Date and time should be in the correct format
|  | Audit Report Phase 2_UAT_SC_001_TC_005 | Verify that the user is able to validate Previous and Current (SMS) in the audit report for the Changed / Modified Phone Number without any selection criteria. |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on Customer Audit Report from General Enquiries/Reports | User should be able to click on the menu
[6 empty] | 3 | Click on find Button. | user should be able to see all the customers who have changed the SMS
[6 empty] | 4 | Verify the Changed / Modified SMS field in the report. | Changed / Modified SMS field should be available in the report.
|  | Audit Report Phase 2_UAT_SC_001_TC_006 | Verify that the user is able to validate Previous and Current (SMS) in the audit report for the Changed / Modified SMS with phone number criteria(In Activity) |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on Customer Audit Report from General Enquiries/Reports | User should be able to click on the menu
[6 empty] | 3 | Select SMS activity option from the drop down and click on Find button. | Report should get loaded successfully with Modified/Changed SMS.
|  | Audit Report Phase 2_UAT_SC_001_TC_007 | Verify that the modified/changed Address is reflecting in the client over view page(T24) |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Navigate to the customer profile | Customer profile should be displayed.
[6 empty] | 3 | Click on edit button and change the address, Validate and commit the deal | Successfully commit the deal.
[6 empty] | 4 | Check the audit and verify the date and time in the audit tab. | Date and time should be in the correct format
|  | Audit Report Phase 2_UAT_SC_001_TC_008 | Verify that the user is able to validate Previous and Current Address in the audit report for the Changed / Modified address without any selection criteria. |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on Customer Audit Report from General Enquiries/Reports | User should be able to click on the menu
[6 empty] | 3 | Click on find Button. | user should be able to see all the customers who have changed the address
[6 empty] | 4 | Verify the Changed / Modified Address field in the report. | Changed / Modified address field should be available in the report.
|  | Audit Report Phase 2_UAT_SC_001_TC_009 | Verify that the user is able to validate Previous and Current Address in the audit report for the Changed / Modified address (Activity)criteria. |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on Customer Audit Report from General Enquiries/Reports | User should be able to click on the menu
[6 empty] | 3 | Select address field option, and click on Find button. | Report should get loaded successfully with Modified/Changed Address.
|  | Audit Report Phase 2_UAT_SC_001_TC_010 | Verify that the modified/changed E-mail ID is reflecting in the client over view page(T24) |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Navigate to the customer profile | Customer profile should be displayed.
[6 empty] | 3 | Edit Email ID, Validate and commit the deal | Successfully commit the deal.
[6 empty] | 4 | Check the audit and verify the date and time in the audit tab. | Date and time should be in the correct format
|  | Audit Report Phase 2_UAT_SC_001_TC_011 | Verify that the user is able to validate Previous and Current E-Mail ID in the audit report for the Changed / Modified E-mail ID without any selection criteria. |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Click on Find Button. | Last 7 days reports should load successfully.
[6 empty] | 4 | Verify the Changed / Modified Email id field in the report. | Changed / Modified E-Mail id field should be available in the report.
|  | Audit Report Phase 2_UAT_SC_001_TC_012 | Verify that the user is able to validate Previous and Current E-Mail ID in the audit report for the Changed / Modified address (Activity) criteria. |  |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully .
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Select E-Mail ID option from the dropdown and click on search button. | Report should get loaded successfully with Modified/Changed E-Mail ID.
|  | Audit Report Phase 2_UAT_SC_001_TC_013 | Verify that the modified/changed TFN/ABN is reflecting in the client over view page(T24) |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Navigate to the customer profile | Customer profile should be displayed.
[6 empty] | 3 | Edit TFN/ABN, Validate and commit the deal | Successfully commit the deal.
[6 empty] | 4 | Check the audit and verify the date and time in the audit tab. | Date and time should be in the correct format
|  | Audit Report Phase 2_UAT_SC_001_TC_014 | Verify that the user is able to validate Previous and Current TFN/ABN in the audit report for the Changed / Modified E-mail ID without any selection criteria. |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Click on Find Button. | Last 7 days reports should load successfully.
[6 empty] | 4 | Verify the Changed / Modified TFN/ABN field in the report. | Changed / Modified TFN/ABN field should be available in the report.
|  | Audit Report Phase 2_UAT_SC_001_TC_015 | Verify that the user is able to validate Previous and Current TFN/ABN in the audit report for the Changed / Modified address (Activity) criteria. |  |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully .
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Select TFN/ABN optionand click on search button. | Report should get loaded successfully with Modified/Changed TFN/ABN.
|  | Audit Report Phase 2_UAT_SC_001_TC_016 | Verify that the Modified Posting Restrict-"Post No Debits" is reflecting in the client over view page(T24) |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Select any customer and click on the posting restriction option, change /modify the posting restriction in the customer overview page. | Customer page should be available and User should be able to edit the posting restriction Successfully.
[6 empty] | 3 | Check the audit and verify the date and time in the audit tab. | Date and time should be in the correct format
|  | Audit Report Phase 2_UAT_SC_001_TC_017 | Verify that the Modified Posting Restrict-"Post No Credits" is reflecting in the client over view page(T24) |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Select any customer and click on the posting restriction option, change /modify the posting restriction in the customer overview page. | Customer page should be available and User should be able to edit the posting restriction Successfully.
[6 empty] | 3 | Check the audit and verify the date and time in the audit tab. | Date and time should be in the correct format
|  | Audit Report Phase 2_UAT_SC_001_TC_018 | Verify that the Modified Posting Restrict-"Post No Entries" is reflecting in the client over view page(T24) |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Select any customer and click on the posting restriction option, change /modify the posting restriction in the customer overview page. | Customer page should be available and User should be able to edit the posting restriction Successfully.
[6 empty] | 3 | Check the audit and verify the date and time in the audit tab. | Date and time should be in the correct format
|  | Audit Report Phase 2_UAT_SC_001_TC_019 | Verify that the user is able to validate the audit report for the Changed / Modified Posting Restrict field without any selection criteria. |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Click on Find Button. | Last 7 days reports should load successfully.
[6 empty] | 4 | Verify the Changed / Modified Posting Restriction field in the report. | Changed / Modified Posting Restriction field should be available in the report.
|  | Audit Report Phase 2_UAT_SC_001_TC_020 | Verify that the user is able to validate the audit report for the Changed / Modified Posting Restrict field with Posting Restrict selection (Activity)criteria. |  |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully .
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Select Posting Restrict option, enter the posting restrict and click on search button. | Report should get loaded successfully with Modified/Changed Posting Restrict.
|  | Audit Report Phase 2_UAT_SC_001_TC_021 | Verify that the Modified Customer name is reflecting in the client over view page(T24) | Corporate Customer |  | 1 | Login to T24. | User should be able to login T24 application Successfully . | As Expected | INPROGRESS
[6 empty] | 2 | Navigate to the customer profile | Customer profile should be displayed.
[6 empty] | 3 | Edit name, Validate and commit the deal | Successfully commit the deal.
[6 empty] | 4 | Check the audit and verify the date and time in the audit tab. | Date and time should be in the correct format
|  | Audit Report Phase 2_UAT_SC_001_TC_022 | Verify that the user is able to validate the audit report for the Changed / Modified Customer name field without any selection criteria. |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully . | As Expected | INPROGRESS
[6 empty] | 2 | Click on Customer Audit Report from General Enquiries/Reports | User should be able to click on the menu
[6 empty] | 3 | Click on find Button. | user should be able to see all the customers who have changed the name
[6 empty] | 4 | Verify the Changed / Modified Customer name field in the report. | Changed / Modified Customer name field should be available in the report.
|  | Audit Report Phase 2_UAT_SC_001_TC_023 | Verify that the user is able to validate the audit report for the Changed / Modified Customer name field with Customer Number selection criteria. |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully . | As Expected | INPROGRESS
[6 empty] | 2 | Click on Customer Audit Report from General Enquiries/Reports | User should be able to click on the menu
[6 empty] | 3 | Enter the customer Number and click on Find button. | Report should get loaded successfully with Modified/Changed customer name.
|  | Audit Report Phase 2_UAT_SC_001_TC_024 | Verify that the modified/changed Phone Number (SMS) is reflecting in the client over view page(T24) |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Navigate to the customer profile | Customer profile should be displayed.
[6 empty] | 3 | Edit Phone Number, Validate and commit the deal | Successfully commit the deal.
[6 empty] | 4 | Check the audit and verify the date and time in the audit tab. | Date and time should be in the correct format
|  | Audit Report Phase 2_UAT_SC_001_TC_025 | Verify that the user is able to validate Previous and Current (SMS) in the audit report for the Changed / Modified Phone Number without any selection criteria. |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on Customer Audit Report from General Enquiries/Reports | User should be able to click on the menu
[6 empty] | 3 | Click on find Button. | user should be able to see all the customers who have changed the SMS
[6 empty] | 4 | Verify the Changed / Modified SMS field in the report. | Changed / Modified SMS field should be available in the report.
|  | Audit Report Phase 2_UAT_SC_001_TC_026 | Verify that the user is able to validate Previous and Current (SMS) in the audit report for the Changed / Modified SMS with phone number criteria(In Activity) |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on Customer Audit Report from General Enquiries/Reports | User should be able to click on the menu
[6 empty] | 3 | Select SMS activity option from the drop down and click on Find button. | Report should get loaded successfully with Modified/Changed SMS.
|  | Audit Report Phase 2_UAT_SC_001_TC_027 | Verify that the modified/changed Address is reflecting in the client over view page(T24) |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Navigate to the customer profile | Customer profile should be displayed.
[6 empty] | 3 | Click on edit button and change the address, Validate and commit the deal | Successfully commit the deal.
[6 empty] | 4 | Check the audit and verify the date and time in the audit tab. | Date and time should be in the correct format
|  | Audit Report Phase 2_UAT_SC_001_TC_028 | Verify that the user is able to validate Previous and Current Address in the audit report for the Changed / Modified address without any selection criteria. |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on Customer Audit Report from General Enquiries/Reports | User should be able to click on the menu
[6 empty] | 3 | Click on find Button. | user should be able to see all the customers who have changed the address
[6 empty] | 4 | Verify the Changed / Modified Address field in the report. | Changed / Modified address field should be available in the report.
|  | Audit Report Phase 2_UAT_SC_001_TC_029 | Verify that the user is able to validate Previous and Current Address in the audit report for the Changed / Modified address (Activity)criteria. |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on Customer Audit Report from General Enquiries/Reports | User should be able to click on the menu
[6 empty] | 3 | Select address field option, and click on Find button. | Report should get loaded successfully with Modified/Changed Address.
|  | Audit Report Phase 2_UAT_SC_001_TC_030 | Verify that the modified/changed E-mail ID is reflecting in the client over view page(T24) |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Navigate to the customer profile | Customer profile should be displayed.
[6 empty] | 3 | Edit Email ID, Validate and commit the deal | Successfully commit the deal.
[6 empty] | 4 | Check the audit and verify the date and time in the audit tab. | Date and time should be in the correct format
|  | Audit Report Phase 2_UAT_SC_001_TC_031 | Verify that the user is able to validate Previous and Current E-Mail ID in the audit report for the Changed / Modified E-mail ID without any selection criteria. |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Click on Find Button. | Last 7 days reports should load successfully.
[6 empty] | 4 | Verify the Changed / Modified Email id field in the report. | Changed / Modified E-Mail id field should be available in the report.
|  | Audit Report Phase 2_UAT_SC_001_TC_032 | Verify that the user is able to validate Previous and Current E-Mail ID in the audit report for the Changed / Modified address (Activity) criteria. |  |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully .
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Select E-Mail ID option from the dropdown and click on search button. | Report should get loaded successfully with Modified/Changed E-Mail ID.
|  | Audit Report Phase 2_UAT_SC_001_TC_033 | Verify that the modified/changed TFN/ABN is reflecting in the client over view page(T24) |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Navigate to the customer profile | Customer profile should be displayed.
[6 empty] | 3 | Edit TFN/ABN, Validate and commit the deal | Successfully commit the deal.
[6 empty] | 4 | Check the audit and verify the date and time in the audit tab. | Date and time should be in the correct format
|  | Audit Report Phase 2_UAT_SC_001_TC_034 | Verify that the user is able to validate Previous and Current TFN/ABN in the audit report for the Changed / Modified E-mail ID without any selection criteria. |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Click on Find Button. | Last 7 days reports should load successfully.
[6 empty] | 4 | Verify the Changed / Modified TFN/ABN field in the report. | Changed / Modified TFN/ABN field should be available in the report.
|  | Audit Report Phase 2_UAT_SC_001_TC_035 | Verify that the user is able to validate Previous and Current TFN/ABN in the audit report for the Changed / Modified address (Activity) criteria. |  |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully .
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Select TFN/ABN optionand click on search button. | Report should get loaded successfully with Modified/Changed TFN/ABN.
|  | Audit Report Phase 2_UAT_SC_001_TC_036 | Verify that the Modified Posting Restrict-"Post No Debits" is reflecting in the client over view page(T24) |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Select any customer and click on the posting restriction option, change /modify the posting restriction in the customer overview page. | Customer page should be available and User should be able to edit the posting restriction Successfully.
[6 empty] | 3 | Check the audit and verify the date and time in the audit tab. | Date and time should be in the correct format
|  | Audit Report Phase 2_UAT_SC_001_TC_037 | Verify that the Modified Posting Restrict-"Post No Credits" is reflecting in the client over view page(T24) |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Select any customer and click on the posting restriction option, change /modify the posting restriction in the customer overview page. | Customer page should be available and User should be able to edit the posting restriction Successfully.
[6 empty] | 3 | Check the audit and verify the date and time in the audit tab. | Date and time should be in the correct format
|  | Audit Report Phase 2_UAT_SC_001_TC_038 | Verify that the Modified Posting Restrict-"Post No Entries" is reflecting in the client over view page(T24) |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Select any customer and click on the posting restriction option, change /modify the posting restriction in the customer overview page. | Customer page should be available and User should be able to edit the posting restriction Successfully.
[6 empty] | 3 | Check the audit and verify the date and time in the audit tab. | Date and time should be in the correct format
|  | Audit Report Phase 2_UAT_SC_001_TC_039 | Verify that the user is able to validate the audit report for the Changed / Modified Posting Restrict field without any selection criteria. |  |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Click on Find Button. | Last 7 days reports should load successfully.
[6 empty] | 4 | Verify the Changed / Modified Posting Restriction field in the report. | Changed / Modified Posting Restriction field should be available in the report.
|  | Audit Report Phase 2_UAT_SC_001_TC_040 | Verify that the user is able to validate the audit report for the Changed / Modified Posting Restrict field with Posting Restrict selection (Activity)criteria. |  |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully .
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Select Posting Restrict option, enter the posting restrict and click on search button. | Report should get loaded successfully with Modified/Changed Posting Restrict.
Audit Report Phase 2 _UAT_SC_002 | Verification of Account Amendments. | Audit Report Phase 2_UAT_SC_002_TC_041 | Verify that the Modified Account Tittle and Statement Preference is reflecting in the account over view page(T24) | Account must be in At call investment |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Select account and click on New activity | New page loaded successfully
[6 empty] | 3 | Select update account details and edit the account tittle | Account tittle changed successfully
[6 empty] | 4 | Select statement opt in/ opt out option | New page loaded successfully
[6 empty] | 5 | Enter the arrangement and click on the find button | Statement opt in/ opt out page loaded successfully
[6 empty] | 6 | Click on the edit button and change the Recipient and supress document option then validate and commit the deal. | Successfully commit the deal.
|  | Audit Report Phase 2_UAT_SC_002_TC_042 | Verify that the user is able to validate the audit report for the Changed / Modified Account Tittle and Statement Preference field without any selection criteria. | Account must be in At call investment |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Click on Find Button. | Last 7 days reports should load successfully.
[6 empty] | 4 | Verify the Changed / Modified product field in the report. | Changed / Modified product field should be available in the report.
|  | Audit Report Phase 2_UAT_SC_002_TC_043 | Verify that the user is able to validate the audit report for the Changed / Modified Account Tittle and Statement Preference field selection criteria. | Account must be in At call investment |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully .
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Select Product option, and click on search button. | Report should get loaded successfully with Modified/Changed product.
|  | Audit Report Phase 2_UAT_SC_002_TC_044 | Verify that the modified/changed Account Tittle and Account Activation Date is reflecting in the account over view page(T24) | Account must be in At Call -Investment Church |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Select account and click on New activity | New page loaded successfully
[6 empty] | 3 | Select update account details and edit the account tittle | Account tittle changed successfully
[6 empty] | 4 | Select any inactive account and click on the arrow button | New page loaded successfully
[6 empty] | 5 | Validate and commit the deal | Overview page staus successfully changed from Inactive to authorised
|  | Audit Report Phase 2_UAT_SC_002_TC_045 | Verify that the user is able to validate Previous and Current Account Tittle and Account Activation Date in the audit report for the Changed / Modified Account Tittle without any selection criteria. | Account must be in At Call -Investment Church |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Click on Find Button. | Last 7 days reports should load successfully.
[6 empty] | 4 | Verify the Changed / Modified account tittle in the report. | Changed / Modified account tittle should be available in the report.
|  | Audit Report Phase 2_UAT_SC_002_TC_046 | Verify that the user is able to validate Previous and Current Account Tittle and Account Activation Date in the audit report for the Changed / Modified Account Tittle and Account Activation Date criteria. | Account must be in At Call -Investment Church |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully .
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Select Account Tittle option, and click on search button. | Report should get loaded successfully with Modified/Changed Account Tittle.
|  | Audit Report Phase 2_UAT_SC_002_TC_047 | Verify that the Modified Account Activation Date (Reset from Inactive) and Roll Change is reflecting in the account over view page(T24) | Account must be in Self Help Settlement Church |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Select any inactive account and click on the arrow button | New page loaded successfully
[6 empty] | 3 | Validate and commit the deal | Overview page staus successfully changed from Inactive to authorised
[6 empty] | 4 | Click on new activity | New page loaded successfully
[6 empty] | 5 | Click on Add/Delete Relation customers | Roll change page loaded successfully
[6 empty] | 6 | Change the roll and validate and commit the deal. | Activation date and roll change Successfully.
|  | Audit Report Phase 2_UAT_SC_002_TC_048 | Verify that the user is able to validate the audit report for the Changed / Modified Account Activation Date field (Reset from Inactive) and Roll Change without any selection criteria. | Account must be in Self Help Settlement Church |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on the Account Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Click on Find Button. | Last 7 days reports should load successfully.
[6 empty] | 4 | Verify the Changed / Modified the activation date and Roll Change in the report. | Changed / Modified activation date and Roll Change field should be available in the report.
|  | Audit Report Phase 2_UAT_SC_002_TC_049 | Verify that the user is able to validate the audit report for the Changed / Modified Account Activation Date field and Roll Change with Activation Date selection criteria. | Account must be in Self Help Settlement Church |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully .
[6 empty] | 2 | Click on the Account Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Select account activation date and roll change from the drop down. | Changed / Modified activation date and Roll Change field should be available in the report.
|  | Audit Report Phase 2_UAT_SC_002_TC_050 | Verify that the modified/changed Single owner to Joint Owner Role is reflecting in the account over view page(T24). | Account must be in Transaction Manager |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on new activity | New page loaded successfully
[6 empty] | 3 | Click on Add/Delete Relation customers | Roll change page loaded successfully
[6 empty] | 4 | Change the roll and validate and commit the deal. | Activation date and roll change Successfully.
|  | Audit Report Phase 2_UAT_SC_002_TC_051 | Verify that the modified/changed Single owner to Guarantor Role is reflecting in the account over view page(T24). | Account must be in Transaction Manager |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on new activity | New page loaded successfully
[6 empty] | 3 | Click on Add/Delete Relation customers | Roll change page loaded successfully
[6 empty] | 4 | Change the roll and validate and commit the deal. | Activation date and roll change Successfully.
|  | Audit Report Phase 2_UAT_SC_002_TC_052 | Verify that the modified/changed Single owner to Signatory Role is reflecting in the account over view page(T24). | Account must be in Transaction Manager |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on new activity | New page loaded successfully
[6 empty] | 3 | Click on Add/Delete Relation customers | Roll change page loaded successfully
[6 empty] | 4 | Change the roll and validate and commit the deal. | Activation date and roll change Successfully.
|  | Audit Report Phase 2_UAT_SC_002_TC_053 | Verify that the modified/changed Joint owner to Guarantor Role is reflecting in the account over view page(T24). | Account must be in At Call Minister and Staff. |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on new activity | New page loaded successfully
[6 empty] | 3 | Click on Add/Delete Relation customers | Roll change page loaded successfully
[6 empty] | 4 | Change the roll and validate and commit the deal. | Activation date and roll change Successfully.
|  | Audit Report Phase 2_UAT_SC_002_TC_054 | Verify that the modified/changed Joint owner to Single owner Role is reflecting in the account over view page(T24). | Account must be in At Call Minister and Staff. |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on new activity | New page loaded successfully
[6 empty] | 3 | Click on Add/Delete Relation customers | Roll change page loaded successfully
[6 empty] | 4 | Change the roll and validate and commit the deal. | Activation date and roll change Successfully.
|  | Audit Report Phase 2_UAT_SC_002_TC_055 | Verify that the modified/changed Joint owner to Signatory Role is reflecting in the account over view page(T24). | Account must be in At Call Minister and Staff. |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on new activity | New page loaded successfully
[6 empty] | 3 | Click on Add/Delete Relation customers | Roll change page loaded successfully
[6 empty] | 4 | Change the roll and validate and commit the deal. | Activation date and roll change Successfully.
|  | Audit Report Phase 2_UAT_SC_002_TC_056 | Verify that the modified/changed Guarantor to Single owner Role is reflecting in the account over view page(T24). | Account must be in Transaction Manager |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on new activity | New page loaded successfully
[6 empty] | 3 | Click on Add/Delete Relation customers | Roll change page loaded successfully
[6 empty] | 4 | Change the roll and validate and commit the deal. | Activation date and roll change Successfully.
|  | Audit Report Phase 2_UAT_SC_002_TC_057 | Verify that the modified/changed Guarantor to Joint owner Role is reflecting in the account over view page(T24). | Account must be in Transaction Manager |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on new activity | New page loaded successfully
[6 empty] | 3 | Click on Add/Delete Relation customers | Roll change page loaded successfully
[6 empty] | 4 | Change the roll and validate and commit the deal. | Activation date and roll change Successfully.
|  | Audit Report Phase 2_UAT_SC_002_TC_058 | Verify that the modified/changed Guarantor to Signatory Role is reflecting in the account over view page(T24). | Account must be in Transaction Manager |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on new activity | New page loaded successfully
[6 empty] | 3 | Click on Add/Delete Relation customers | Roll change page loaded successfully
[6 empty] | 4 | Change the roll and validate and commit the deal. | Activation date and roll change Successfully.
|  | Audit Report Phase 2_UAT_SC_002_TC_059 | Verify that the modified/changed Signatory to Single owner Role is reflecting in the account over view page(T24). | Account must be in Self Help Settlement Church |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on new activity | New page loaded successfully
[6 empty] | 3 | Click on Add/Delete Relation customers | Roll change page loaded successfully
[6 empty] | 4 | Change the roll and validate and commit the deal. | Activation date and roll change Successfully.
|  | Audit Report Phase 2_UAT_SC_002_TC_060 | Verify that the modified/changed Signatory to Joint owner Role is reflecting in the account over view page(T24). | Account must be in Self Help Settlement Church |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on new activity | New page loaded successfully
[6 empty] | 3 | Click on Add/Delete Relation customers | Roll change page loaded successfully
[6 empty] | 4 | Change the roll and validate and commit the deal. | Activation date and roll change Successfully.
|  | Audit Report Phase 2_UAT_SC_002_TC_061 | Verify that the modified/changed Signatory to Guarantor Role is reflecting in the account over view page(T24). | Account must be in Self Help Settlement Church |  | 1 | Login to T24. | User should be able to login T24 application Successfully .
[6 empty] | 2 | Click on new activity | New page loaded successfully
[6 empty] | 3 | Click on Add/Delete Relation customers | Roll change page loaded successfully
[6 empty] | 4 | Change the roll and validate and commit the deal. | Activation date and roll change Successfully.
|  | Audit Report Phase 2_UAT_SC_002_TC_062 | Verify that the user is able to validate Previous and Current Role in the audit report for the Changed / Modified Role without any selection criteria. |  |  |  | Login to T24. | User should be able to login T24 application Successfully . | As Expected
[7 empty] | Click on the Audit log option. | Audit log option should be accessible.
[7 empty] | Click on Find Button. | Last 7 days reports should load successfully.
[7 empty] | Verify the Changed / Modified Role field in the report. | Changed / Modified role field should be available in the report.
|  | Audit Report Phase 2_UAT_SC_002_TC_063 | Verify that the user is able to validate Previous and Current Role in the audit report for the Changed / Modified Role criteria. |  |  |  | Load the T24 Application. | User should be able to launch the T24 application Successfully . | As Expected
[7 empty] | Click on the Audit log option. | Audit log option should be accessible.
[7 empty] | Select Role option click on search button. | Report should get loaded successfully with Modified/Changed Role.
|  | Audit Report Phase 2_UAT_SC_002_TC_064 | Verify that the modified/changed the below Account Tittle is reflecting in the account over view page(T24) i.Account Tittle 1 ii.Account Tittle 2 iii.Short Tittle iv.Mnemonic | Account must be in Transaction Manager |  | 1 | Login to T24. | User should be able to login T24 application Successfully . | As Expected
[6 empty] | 2 | Select account and click on New activity | New page loaded successfully
[6 empty] | 3 | Select update account details and edit the account tittle | Account tittle changed successfully
[6 empty] | 4 | Validate and commit the deal | Should be able to get the audit log successfully
|  | Audit Report Phase 2_UAT_SC_002_TC_065 | Verify that the user is able to validate the audit report for the Changed / Modified the below Account Tittle field without any selection criteria. i.Account Tittle 1 ii.Account Tittle 2 iii.Short Tittle iv.Mnemonic | Account must be in Transaction Manager |  | 1 | Login to T24. | User should be able to login T24 application Successfully . | As Expected
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Click on Find Button. | Last 7 days reports should load successfully.
[6 empty] | 4 | Verify the Changed / Modified field in the report. | Changed / Modified field should be available in the report.
|  | Audit Report Phase 2_UAT_SC_002_TC_066 | Verify that the user is able to validate the audit report for the Changed / Modified the below Account Tittle selection criteria. i.Account Tittle 1 ii.Account Tittle 2 iii.Short Tittle iv.Mnemonic | Account must be in Transaction Manager |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully . | As Expected
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Select the activity from the drop down and click on search button. | Report should get loaded successfully with Modified/Changed product.
|  | Audit Report Phase 2_UAT_SC_002_TC_067 | Verify that the modified/changed the below fields are reflecting in the account over view page(T24) i.Customer Role ii.Tax Liability Percentage | Account must be in Self help investment Church |  | 1 | Login to T24. | User should be able to login T24 application Successfully . | As Expected
[6 empty] | 2 | Click on new activity | New page loaded successfully
[6 empty] | 3 | Click on Add/Delete Relation customers | Roll change page loaded successfully
[6 empty] | 4 | Change the roll and validate and commit the deal. | Activation date and roll change Successfully.
|  | Audit Report Phase 2_UAT_SC_002_TC_068 | Verify that the modified/changed the below fields are reflecting in the audit report without any selection criteria. i.Customer Role ii.Tax Liability Percentage | Account must be in Self help investment Church |  | 1 | Login to T24. | User should be able to login T24 application Successfully . | As Expected
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Click on Find Button. | Last 7 days reports should load successfully.
|  | Audit Report Phase 2_UAT_SC_002_TC_069 | Verify that the modified/changed the below fields are reflecting in the account over view page(T24) with selection criteria of customer role and tax liability percentage. | Account must be in Self help investment Church |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully . | As Expected
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Select activity from the drop down and click on search button. | Report should get loaded successfully with Modified/Changed product.
|  | Audit Report Phase 2_UAT_SC_002_TC_070 | Verify that the modified/changed the below fields are reflecting in the account over view page(T24) i.Customer Role ii.Tax Liability Percentage | Account must be in At Call Minister and Staff |  | 1 | Login to T24. | User should be able to login T24 application Successfully . | As Expected
[6 empty] | 2 | Click on new activity | New page loaded successfully
[6 empty] | 3 | Click on Add/Delete Relation customers | Roll change page loaded successfully
[6 empty] | 4 | Change the roll and validate and commit the deal. | Activation date and roll change Successfully.
|  | Audit Report Phase 2_UAT_SC_002_TC_071 | Verify that the modified/changed the below fields are reflecting in the account over view page(T24) with selection and without selection criteria . | Account must be in At Call Minister and Staff |  | 1 | Login to T24. | User should be able to login T24 application Successfully . | As Expected
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Click on Find Button. | Last 7 days reports should load successfully.
Audit Report Phase 2 _UAT_SC_003 | Verification of Deposits Amendments. | Audit Report Phase 2_UAT_SC_003_TC_072 | Verify that the Modified Account Tittle and Statement Preference is reflecting in the deposit over view page(T24) | Deposit must be Fixed term church |  | 1 | Login to T24. | User should be able to login T24 application Successfully . | As Expected
[6 empty] | 2 | Select account and click on New activity | New page loaded successfully
[6 empty] | 3 | Select update account details and edit the account tittle | Account tittle changed successfully
[6 empty] | 4 | Select statement opt in/ opt out option | New page loaded successfully
[6 empty] | 5 | Enter the arrangement and click on the find button | Statement opt in/ opt out page loaded successfully
[6 empty] | 6 | Click on the edit button and change the Recipient and supress document option then validate and commit the deal. | Successfully commit the deal.
|  | Audit Report Phase 2_UAT_SC_003_TC_073 | Verify that the user is able to validate the audit report for the Changed / Modified Account Tittle and Statement Preference field without any selection criteria. | Deposit must be Fixed term church |  | 1 | Login to T24. | User should be able to login T24 application Successfully . | As Expected
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Click on Find Button. | Last 7 days reports should load successfully.
[6 empty] | 4 | Verify the Changed / Modified product field in the report. | Changed / Modified product field should be available in the report.
|  | Audit Report Phase 2_UAT_SC_003_TC_074 | Verify that the user is able to validate the audit report for the Changed / Modified Account Tittle and Statement Preference field selection criteria. | Deposit must be Fixed term church |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully . | As Expected
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Select Product option, and click on search button. | Report should get loaded successfully with Modified/Changed product.
|  | Audit Report Phase 2_UAT_SC_003_TC_075 | Verify that the modified/changed Account Tittle and Roll change is reflecting in the account over view page(T24) | Deposit must be FTI Non Church Annually |  | 1 | Login to T24. | User should be able to login T24 application Successfully . | As Expected
[6 empty] | 2 | Select account and click on New activity | New page loaded successfully
[6 empty] | 3 | Select update account details and edit the account tittle | Account tittle changed successfully
[6 empty] | 4 | Click on new activity | New page loaded successfully
[6 empty] | 5 | Click on Add/Delete Relation customers | Roll change page loaded successfully
[6 empty] | 6 | Change the roll and validate and commit the deal. | Activation date and roll change Successfully.
|  | Audit Report Phase 2_UAT_SC_003_TC_076 | Verify that the user is able to validate Previous and Current Account Tittle and Roll change in the audit report for the Changed / Modified Account Tittle and Roll Change without any selection criteria. | Deposit must be FTI Annually |  | 1 | Login to T24. | User should be able to login T24 application Successfully . | As Expected
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Click on Find Button. | Last 7 days reports should load successfully.
[6 empty] | 4 | Verify the Changed / Modified account tittle and roll change in the report. | Changed / Modified account tittle and roll change should be available in the report.
|  | Audit Report Phase 2_UAT_SC_003_TC_077 | Verify that the user is able to validate Previous and Current Account Tittle and Roll Changein the audit report for the Changed / Modified Account Tittle and Roll Change with selection criteria. | Deposit must be FTI Annually |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully . | As Expected
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Select account tittle and roll change click on search button. | Report should get loaded successfully with Modified/Changed Account Tittle and roll change.
|  | Audit Report Phase 2_UAT_SC_003_TC_078 | Verify that the modified/changed the below Account Tittle is reflecting in the account over view page(T24) i.Account Tittle 1 ii.Account Tittle 2 iii.Short Tittle iv.Mnemonic | Deposit must be Uniting Fixed Term Investment |  | 1 | Login to T24. | User should be able to login T24 application Successfully . | As Expected
[6 empty] | 2 | Select account and click on New activity | New page loaded successfully
[6 empty] | 3 | Select update account details and edit the account tittle | Account tittle changed successfully
[6 empty] | 4 | Validate and commit the deal | Should be able to get the audit log successfully
[6 empty] | 1 | Login to T24. | User should be able to login T24 application Successfully .
|  | Audit Report Phase 2_UAT_SC_003_TC_079 | Verify that the user is able to validate the audit report for the Changed / Modified the below Account Tittle field without any selection criteria. i.Account Tittle 1 ii.Account Tittle 2 iii.Short Tittle iv.Mnemonic | Deposit must be Uniting Fixed Term Investment |  | 2 | Click on the Audit log option. | Audit log option should be accessible. | As Expected
[6 empty] | 3 | Click on Find Button. | Last 7 days reports should load successfully.
[6 empty] | 4 | Verify the Changed / Modified field in the report. | Changed / Modified field should be available in the report.
|  | Audit Report Phase 2_UAT_SC_003_TC_080 | Verify that the user is able to validate the audit report for the Changed / Modified the below Account Tittle f selection criteria. i.Account Tittle 1 ii.Account Tittle 2 iii.Short Tittle iv.Mnemonic | Deposit must be Uniting Fixed Term Investment |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully .
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible. | As Expected
[6 empty] | 3 | Select the activity from the drop down and click on search button. | Report should get loaded successfully with Modified/Changed product.
|  | Audit Report Phase 2_UAT_SC_003_TC_081 | Verify that the modified/changed the below fields are reflecting in the deposit over view page(T24) i.Customer Role ii.Tax Liability Percentage | Deposit must be FTI Monthly |  | 1 | Login to T24. | User should be able to login T24 application Successfully . | As Expected
[6 empty] | 2 | Click on new activity | New page loaded successfully
[6 empty] | 3 | Click on Add/Delete Relation customers | Roll change page loaded successfully
[6 empty] | 4 | Change the roll and validate and commit the deal. | Activation date and roll change Successfully.
|  | Audit Report Phase 2_UAT_SC_003_TC_082 | Verify that the user is able to validate the audit report for the Changed / Modified the below field without any selection criteria. i.Customer Role ii.Tax Liability Percentage | Deposit must be FTI Monthly |  | 1 | Login to T24. | User should be able to login T24 application Successfully . | As Expected
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Click on Find Button. | Last 7 days reports should load successfully.
|  | Audit Report Phase 2_UAT_SC_003_TC_083 | Verify that the user is able to validate the audit report for the Changed / Modified the below selection criteria. i.Customer Role ii.Tax Liability Percentage | Deposit must be FTI Monthly |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully . | As Expected
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Select activity from the drop down and click on search button. | Report should get loaded successfully with Modified/Changed product.
Audit Report Phase 2 _UAT_SC_004 | Verification of Loan Amendments. | Audit Report Phase 2_UAT_SC_004_TC_084 | Verify that the Modified Account Tittle and Statement Preference is reflecting in the loan over view page(T24) | Loan must be in church loan. |  | 1 | Login to T24. | User should be able to login T24 application Successfully . | As Expected
[6 empty] | 2 | Select account and click on New activity | New page loaded successfully
[6 empty] | 3 | Select update account details and edit the account tittle | Account tittle changed successfully
[6 empty] | 4 | Select statement opt in/ opt out option | New page loaded successfully
[6 empty] | 5 | Enter the arrangement and click on the find button | Statement opt in/ opt out page loaded successfully
[6 empty] | 6 | Click on the edit button and change the Recipient and supress document option then validate and commit the deal. | Successfully commit the deal.
|  | Audit Report Phase 2_UAT_SC_004_TC_085 | Verify that the user is able to validate the audit report for the Changed / Modified Account Tittle and Statement Preference field without any selection criteria. | Loan must be in church loan. |  | 1 | Login to T24. | User should be able to login T24 application Successfully . | As Expected
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Click on Find Button. | Last 7 days reports should load successfully.
[6 empty] | 4 | Verify the Changed / Modified product field in the report. | Changed / Modified product field should be available in the report.
|  | Audit Report Phase 2_UAT_SC_004_TC_086 | Verify that the user is able to validate the audit report for the Changed / Modified Account Tittle and Statement Preference field selection criteria. | Loan must be in church loan. |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully . | As Expected
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Select Product option, and click on search button. | Report should get loaded successfully with Modified/Changed product.
|  | Audit Report Phase 2_UAT_SC_004_TC_087 | Verify that the modified/changed Account Tittle and Roll change is reflecting in the loan over view page(T24) | Loan must be in commercial loan |  | 1 | Login to T24. | User should be able to login T24 application Successfully . | As Expected
[6 empty] | 2 | Select account and click on New activity | New page loaded successfully
[6 empty] | 3 | Select update account details and edit the account tittle | Account tittle changed successfully
[6 empty] | 4 | Click on new activity | New page loaded successfully
[6 empty] | 5 | Click on Add/Delete Relation customers | Roll change page loaded successfully
[6 empty] | 6 | Change the roll and validate and commit the deal. | Activation date and roll change Successfully.
|  | Audit Report Phase 2_UAT_SC_004_TC_088 | Verify that the user is able to validate Previous and Current Account Tittle and Roll change in the audit report for the Changed / Modified Account Tittle and Roll Change without any selection criteria. | Loan must be in commercial loan |  | 1 | Login to T24. | User should be able to login T24 application Successfully . | As Expected
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Click on Find Button. | Last 7 days reports should load successfully.
[6 empty] | 4 | Verify the Changed / Modified account tittle and roll change in the report. | Changed / Modified account tittle and roll change should be available in the report.
|  | Audit Report Phase 2_UAT_SC_004_TC_089 | Verify that the user is able to validate Previous and Current Account Tittle and Roll Change in the audit report for the Changed / Modified Account Tittle and Roll Change criteria.. | Loan must be in commercial loan |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully . | As Expected
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Select account tittle and roll change click on search button. | Report should get loaded successfully with Modified/Changed Account Tittle and roll change.
|  | Audit Report Phase 2_UAT_SC_004_TC_090 | Verify that the modified/changed the below Account Tittle is reflecting in the loan over view page(T24) i.Account Tittle 1 ii.Account Tittle 2 iii.Short Tittle iv.Mnemonic | Loan must be in Housing Loan. |  | 1 | Login to T24. | User should be able to login T24 application Successfully . | As Expected
[6 empty] | 2 | Select account and click on New activity | New page loaded successfully
[6 empty] | 3 | Select update account details and edit the account tittle | Account tittle changed successfully
[6 empty] | 4 | Validate and commit the deal | Should be able to get the audit log successfully
|  | Audit Report Phase 2_UAT_SC_004_TC_091 | Verify that the user is able to validate the audit report for the Changed / Modified the below Account Tittle field without any selection criteria. i.Account Tittle 1 ii.Account Tittle 2 iii.Short Tittle iv.Mnemonic | Loan must be in Housing Loan. |  | 1 | Login to T24. | User should be able to login T24 application Successfully . | As Expected
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Click on Find Button. | Last 7 days reports should load successfully.
[6 empty] | 4 | Verify the Changed / Modified field in the report. | Changed / Modified field should be available in the report.
|  | Audit Report Phase 2_UAT_SC_004_TC_092 | Verify that the user is able to validate the audit report for the Changed / Modified the below Account Tittle selection criteria. i.Account Tittle 1 ii.Account Tittle 2 iii.Short Tittle iv.Mnemonic | Loan must be in Housing Loan. |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully . | As Expected
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Select the activity from the drop down and click on search button. | Report should get loaded successfully with Modified/Changed product.
|  | Audit Report Phase 2_UAT_SC_004_TC_093 | Verify that the modified/changed the below fields are reflecting in the loan over view page(T24) i.Customer Role ii.Tax Liability Percentage | Loan must be in personal loan. |  | 1 | Login to T24. | User should be able to login T24 application Successfully . | As Expected
[6 empty] | 2 | Click on new activity | New page loaded successfully
[6 empty] | 3 | Click on Add/Delete Relation customers | Roll change page loaded successfully
[6 empty] | 4 | Change the roll and validate and commit the deal. | Activation date and roll change Successfully.
|  | Audit Report Phase 2_UAT_SC_004_TC_094 | Verify that the user is able to validate the audit report for the Changed / Modified the below field without any selection criteria. i.Customer Role ii.Tax Liability Percentage | Loan must be in personal loan. |  | 1 | Login to T24. | User should be able to login T24 application Successfully . | As Expected
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Click on Find Button. | Last 7 days reports should load successfully.
|  | Audit Report Phase 2_UAT_SC_004_TC_095 | Verify that the user is able to validate the audit report for the Changed / Modified the below selection criteria. i.Customer Role ii.Tax Liability Percentage | Loan must be in personal loan. |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully . | As Expected
[6 empty] | 2 | Click on the Audit log option. | Audit log option should be accessible.
[6 empty] | 3 | Select activity from the drop down and click on search button. | Report should get loaded successfully with Modified/Changed product.
Audit Report Phase 2 _UAT_SC_005 | Amendment Report verification | Audit Report Phase 2_UAT_SC_005_TC_096 | Verify that the Customer amendment report with activity criteria as SMS Change and Audit date greater than or equals to 20 June 2021, system should list all customers Phone number changed from 20 June 2021. |  |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully .
[6 empty] | 2 | Click on Customer Audit Report | New page loaded successfully
[6 empty] | 3 | Select SMS activity option from the drop down, select the date and click on Find button. | Amendment report loaded successfully
|  | Audit Report Phase 2_UAT_SC_005_TC_097 | Verify that the Account amendment report with activity criteria as Statement preference change and effective date greater than or equals to 30 July 2021, system should list all accounts amended after 30th July 2021 by updating account title. |  |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully .
[6 empty] | 2 | Click on Customer Audit Report | New page loaded successfully
[6 empty] | 3 | Select stataement preference activity option from the drop down, select the date and click on Find button. | Amendment report loaded successfully
|  | Audit Report Phase 2_UAT_SC_005_TC_098 | Verify that the Account amendment report with activity criteria as Account Title Change and effective date greater than or equals to 30 July 2021, system should list all deposits amended after 30th July 2021 by updating account title. |  |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully .
[6 empty] | 2 | Click on Customer Audit Report | New page loaded successfully
[6 empty] | 3 | Select Account Tittle activity option from the drop down, select the date and click on Find button. | Amendment report loaded successfully
|  | Audit Report Phase 2_UAT_SC_005_TC_099 | Verify that the Account amendment report with activity criteria as Account Title Change and effective date greater than or equals to 30 July 2021, system should list all loans amended after 30th July 2021 by updating account title. |  |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully .
[6 empty] | 2 | Click on Customer Audit Report | New page loaded successfully
[6 empty] | 3 | Select Account Tittle activity option from the drop down, select the date and click on Find button. | Amendment report loaded successfully
|  | Audit Report Phase 2_UAT_SC_005_TC_100 | Verify that the Account amendment report with activity criteria as Account Activation Date and effective date greater than or equals to 30 July 2021, system should list all account amended after 30th July 2021 by updating account title. |  |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully .
[6 empty] | 2 | Click on Customer Audit Report | New page loaded successfully
[6 empty] | 3 | Select Account Activation Date activity option from the drop down, select the date and click on Find button. | Amendment report loaded successfully
|  | Audit Report Phase 2_UAT_SC_005_TC_101 | Verify that the Account amendment report with activity criteria as Statement preference change and effective date greater than or equals to 30 July 2021, system should list all loan amended after 30th July 2021 by statement preference. |  |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully .
[6 empty] | 2 | Click on Customer Audit Report | New page loaded successfully
[6 empty] | 3 | Select stataement preference activity option from the drop down, select the date and click on Find button. | Amendment report loaded successfully
|  | Audit Report Phase 2_UAT_SC_005_TC_102 | Verify that the Account amendment report with activity criteria as Roll change and effective date greater than or equals to 30 July 2021, system should list all Deposits amended after 30th July 2021 by updating roll change. |  |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully .
[6 empty] | 2 | Click on Customer Audit Report | New page loaded successfully
[6 empty] | 3 | Select RollChange activity option from the drop down, select the date and click on Find button. | Amendment report loaded successfully
|  | Audit Report Phase 2_UAT_SC_005_TC_103 | Verify the customer amendment report using through sector code |  |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully .
[6 empty] | 2 | Click on Customer Audit Report | Customer Audit Report page loaded successfully
[6 empty] | 3 | Select sectorcode option from the drop down, select the date and click on Find button. | Amendment report loaded successfully
Audit Report Phase 2 _UAT_SC_006 | Drop Down verification | Audit Report Phase 2_UAT_SC_006_TC_104 | Verify user is able to check the param table and below options are available in the drop down list •SMS change • Address change • Email ID change • TFN or ABN change • posting restriction • Update Customer • Update Account • Statement Preference Changed • Account activation |  |  | 1 | Load the T24 Application. | User should be able to launch the T24 application Successfully .
[6 empty] | 2 | Click on Customer Audit or Account Audit Report | Customer Audit Report page loaded successfully
[6 empty] | 3 | Click on the drop down button verify the activity | Options are available in the drop down
Audit Report Phase 2 _UAT_SC_007 | Menu verification | Audit Report Phase 2_UAT_SC_007_TC_105 | Verify whether the below newly menus are available under the general enquiries i.Customer Audit Report ii.Account Audit Report |  |  | 1 | Login to T24 Application. | T24 should be logged in Successfully.
[6 empty] | 2 | Click on the general enquiries and check the newly menus are available or not. | Newly menus should be available under the general enquiries.
Audit Report Phase 2 _UAT_SC_008 | Activity dropdown verification in customer amendments | Audit Report Phase 2_UAT_SC_008_TC_106 | Verify that the customer audit report enquiry shows only address change amendements when the selection criteria is AddressChange |  |  | 1 | Login to T24 Application. | T24 should be logged in Successfully.
[6 empty] | 2 | Click on Customer Audit Report | Customer Audit Report page loaded successfully
[6 empty] | 3 | Select AddressChange activity option from the dropdown | Should be loaded addresschange activitys only
|  | Audit Report Phase 2_UAT_SC_008_TC_107 | Verify that the customer audit report enquiry shows only address change amendements when the selection criteria is EmailidChange |  |  | 1 | Login to T24 Application. | T24 should be logged in Successfully.
[6 empty] | 2 | Click on Customer Audit Report | Customer Audit Report page loaded successfully
[6 empty] | 3 | Select Emailchange activity option from the dropdown | Should be loaded Emailchange activitys only
|  | Audit Report Phase 2_UAT_SC_008_TC_108 | Verify that the customer audit report enquiry shows only address change amendements when the selection criteria is Phonesmschange |  |  | 1 | Login to T24 Application. | T24 should be logged in Successfully.
[6 empty] | 2 | Click on Customer Audit Report | Customer Audit Report page loaded successfully
[6 empty] | 3 | Select Phonesmschange activity option from the dropdown | Should be loaded Phonesmschange activitys only
|  | Audit Report Phase 2_UAT_SC_008_TC_109 | Verify that the customer audit report enquiry shows only address change amendements when the selection criteria is postingrestriction |  |  | 1 | Login to T24 Application. | T24 should be logged in Successfully.
[6 empty] | 2 | Click on Customer Audit Report | Customer Audit Report page loaded successfully
[6 empty] | 3 | Select postingrestriction activity option from the dropdown | Should be loaded postingrestriction activitys only
|  | Audit Report Phase 2_UAT_SC_008_TC_110 | Verify that the customer audit report enquiry shows only address change amendements when the selection criteria is TFNorABNChange |  |  | 1 | Login to T24 Application. | T24 should be logged in Successfully.
[6 empty] | 2 | Click on Customer Audit Report | Customer Audit Report page loaded successfully
[6 empty] | 3 | Select TFNorABN Change activity option from the dropdown | Should be loaded TFNorABN Change activitys only
|  | Audit Report Phase 2_UAT_SC_008_TC_111 | Verify that the customer audit report enquiry shows only address change amendements when the selection criteria is UpdateCustomer |  |  | 1 | Login to T24 Application. | T24 should be logged in Successfully.
[6 empty] | 2 | Click on Customer Audit Report | Customer Audit Report page loaded successfully
[6 empty] | 3 | Select UpdateCustomer activity option from the dropdown | Should be loaded UpdateCustomer activitys only
Audit Report Phase 2 _UAT_SC_009 | Activity dropdown verification in accountamendments | Audit Report Phase 2_UAT_SC_009_TC_112 | Verify that the accountaudit report enquiry shows only rolechange amendements when the selection criteria is RoleChange |  |  | 1 | Login to T24 Application. | T24 should be logged in Successfully.
[6 empty] | 2 | Click on Account Audit Report | Account Audit Report page loaded successfully
[6 empty] | 3 | Select Rolechange activity option from the dropdown | Should be loaded Rolechange activitys only
|  | Audit Report Phase 2_UAT_SC_009_TC_113 | Verify that the accountaudit report enquiry shows only rolechange amendements when the selection criteria is StatementPreference |  |  | 1 | Login to T24 Application. | T24 should be logged in Successfully.
[6 empty] | 2 | Click on Account Audit Report | Account Audit Report page loaded successfully
[6 empty] | 3 | Select statementpreference activity option from the dropdown | Should be loaded statementpreference activitys only
|  | Audit Report Phase 2_UAT_SC_009_TC_114 | Verify that the accountaudit report enquiry shows only rolechange amendements when the selection criteria isUpdateAccount |  |  | 1 | Login to T24 Application. | T24 should be logged in Successfully.
[6 empty] | 2 | Click on Account Audit Report | Account Audit Report page loaded successfully
[6 empty] | 3 | Select UpdateAccount activity option from the dropdown | Should be loaded UpdateAccount activitys only

## Overall Execution
SCENARIO ID | SCENARIO NAME | TESTCASE ID | STATUS | EXCECUTED BY | DATE | SCENARIO ID | SCENARIO NAME | TESTCASE ID | STATUS | EXCECUTED BY | DATE | REMARKS | SCENARIO ID | SCENARIO NAME | TESTCASE ID | STATUS | EXCECUTED BY | Date | SCENARIO ID | SCENARIO NAME | TESTCASE ID | STATUS | EXCECUTED BY | DATE | SCENARIO ID | SCENARIO NAME | TESTCASE ID | STATUS | EXCECUTED BY | DATE | SCENARIO ID | SCENARIO NAME | TESTCASE ID | STATUS | EXCECUTED BY | DATE | SCENARIO ID | SCENARIO NAME | TESTCASE ID | STATUS | EXCECUTED BY | DATE | SCENARIO ID | SCENARIO NAME | TESTCASE ID | STATUS | EXCECUTED BY | DATE | SCENARIO ID | SCENARIO NAME | TESTCASE ID | STATUS | EXCECUTED BY | DATE
CR4_SC_001 | Verification of Customer Amendments. | CR4_SC_001_TC_001 | PASS | AKHILA | 26.12.2024 | CR4_SC_002 | Verification of Account Amendments. | CR4_SC_002_TC_041 | PASS | AKHILA | 26.12.2024 |  | CR4_SC_003 | Verification of Deposits Amendments. | CR4_SC_003_TC_072 | PASS | AKHILA | 27.12.2024 | CR4_SC_004 | Verification of Loan Amendments. | CR4_SC_004_TC_084 | PASS | AKHILA | 31.12.2024 | CR4_SC_005 | Amendment Report verification | CR4_SC_005_TC_096 | PASS | AKHILA | 31.12.2024 | CR4_SC_006 | Param Table verification | CR4_SC_006_TC_104 | PASS | AKHILA | 31.12.2024 | CR4_SC_007 | Menu verification | CR4_SC_007_TC_105 | PASS | AKHILA | 31.12.2024 | CR4_SC_008 | Activity dropdown verification in customer amendments | CR4_SC_008_TC_106 | FAIL | AKHILA | 31.12.2024 | CR4_SC_009 | Activity dropdown verification in Account amendments | CR4_SC_009_TC_112 | PASS | AKHILA | 31.12.2024
|  | CR4_SC_001_TC_002 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_042 | PASS | AKHILA | 26.12.2024 |  |  |  | CR4_SC_003_TC_073 | PASS | AKHILA | 27.12.2024 |  |  | CR4_SC_004_TC_085 | PASS | AKHILA | 31.12.2024 |  |  | CR4_SC_005_TC_097 | PASS | AKHILA | 31.12.2024 | [14 empty] | CR4_SC_008_TC_107 | BLOCKED | AKHILA | 31.12.2024 |  |  | CR4_SC_009_TC_113 | PASS | AKHILA | 31.12.2024
|  | CR4_SC_001_TC_003 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_043 | PASS | AKHILA | 26.12.2024 |  |  |  | CR4_SC_003_TC_074 | PASS | AKHILA | 27.12.2024 |  |  | CR4_SC_004_TC_086 | PASS | AKHILA | 31.12.2024 |  |  | CR4_SC_005_TC_098 | PASS | AKHILA | 31.12.2024 | [14 empty] | CR4_SC_008_TC_108 | BLOCKED | AKHILA | 31.12.2024 |  |  | CR4_SC_009_TC_114 | PASS | AKHILA | 31.12.2024
|  | CR4_SC_001_TC_004 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_044 | PASS | AKHILA | 06.01.2025 |  |  |  | CR4_SC_003_TC_075 | PASS | AKHILA | 27.12.2024 |  |  | CR4_SC_004_TC_087 | PASS | AKHILA | 31.12.2024 |  |  | CR4_SC_005_TC_099 | PASS | AKHILA | 31.12.2024 | [14 empty] | CR4_SC_008_TC_109 | PASS | AKHILA | 31.12.2024
|  | CR4_SC_001_TC_005 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_045 | PASS | AKHILA | 06.01.2025 | Account Activation Date |  |  | CR4_SC_003_TC_076 | PASS | AKHILA | 27.12.2024 |  |  | CR4_SC_004_TC_088 | PASS | AKHILA | 31.12.2024 |  |  | CR4_SC_005_TC_100 | PASS | AKHILA | 06.01.2025 | [14 empty] | CR4_SC_008_TC_110 | BLOCKED | AKHILA | 31.12.2024
|  | CR4_SC_001_TC_006 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_046 | PASS | AKHILA | 06.01.2025 | Account Activation Date |  |  | CR4_SC_003_TC_077 | PASS | AKHILA | 27.12.2024 |  |  | CR4_SC_004_TC_089 | PASS | AKHILA | 31.12.2024 |  |  | CR4_SC_005_TC_101 | PASS | AKHILA | 31.12.2024 | [14 empty] | CR4_SC_008_TC_111 | BLOCKED | AKHILA | 31.12.2024
|  | CR4_SC_001_TC_007 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_047 | PASS | AKHILA | 06.01.2025 | Account Activation Date |  |  | CR4_SC_003_TC_078 | PASS | AKHILA | 27.12.2024 |  |  | CR4_SC_004_TC_090 | PASS | AKHILA | 31.12.2024 |  |  | CR4_SC_005_TC_102 | PASS | AKHILA | 31.12.2024
|  | CR4_SC_001_TC_008 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_048 | PASS | AKHILA | 06.01.2025 | Account Activation Date |  |  | CR4_SC_003_TC_079 | PASS | AKHILA | 27.12.2024 |  |  | CR4_SC_004_TC_091 | PASS | AKHILA | 31.12.2024 |  |  | CR4_SC_005_TC_103 | PASS | AKHILA | 31.12.2024
|  | CR4_SC_001_TC_009 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_049 | PASS | AKHILA | 06.01.2025 | Account Activation Date |  |  | CR4_SC_003_TC_080 | PASS | AKHILA | 27.12.2024 |  |  | CR4_SC_004_TC_092 | PASS | AKHILA | 31.12.2024
|  | CR4_SC_001_TC_010 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_050 | PASS | AKHILA | 27.12.2024 |  |  |  | CR4_SC_003_TC_081 | PASS | AKHILA | 31.12.2024 |  |  | CR4_SC_004_TC_093 | PASS | AKHILA | 31.12.2024
|  | CR4_SC_001_TC_011 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_051 | PASS | AKHILA | 27.12.2024 |  |  |  | CR4_SC_003_TC_082 | PASS | AKHILA | 31.12.2024 |  |  | CR4_SC_004_TC_094 | PASS | AKHILA | 31.12.2024
|  | CR4_SC_001_TC_012 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_052 | PASS | AKHILA | 27.12.2024 |  |  |  | CR4_SC_003_TC_083 | PASS | AKHILA | 31.12.2024 |  |  | CR4_SC_004_TC_095 | PASS | AKHILA | 31.12.2024
|  | CR4_SC_001_TC_013 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_053 | PASS | AKHILA | 27.12.2024
|  | CR4_SC_001_TC_014 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_054 | PASS | AKHILA | 27.12.2024
|  | CR4_SC_001_TC_015 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_055 | PASS | AKHILA | 27.12.2024
|  | CR4_SC_001_TC_016 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_056 | PASS | AKHILA | 27.12.2024
|  | CR4_SC_001_TC_017 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_057 | PASS | AKHILA | 27.12.2024
|  | CR4_SC_001_TC_018 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_058 | PASS | AKHILA | 27.12.2024
|  | CR4_SC_001_TC_019 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_059 | PASS | AKHILA | 27.12.2024
|  | CR4_SC_001_TC_020 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_060 | PASS | AKHILA | 27.12.2024
|  | CR4_SC_001_TC_021 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_061 | PASS | AKHILA | 27.12.2024
|  | CR4_SC_001_TC_022 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_062 | PASS | AKHILA | 27.12.2024
|  | CR4_SC_001_TC_023 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_063 | PASS | AKHILA | 27.12.2024
|  | CR4_SC_001_TC_024 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_064 | PASS | AKHILA | 27.12.2024
|  | CR4_SC_001_TC_025 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_065 | PASS | AKHILA | 27.12.2024
|  | CR4_SC_001_TC_026 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_066 | PASS | AKHILA | 27.12.2024
|  | CR4_SC_001_TC_027 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_067 | PASS | AKHILA | 27.12.2024
|  | CR4_SC_001_TC_028 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_068 | PASS | AKHILA | 27.12.2024
|  | CR4_SC_001_TC_029 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_069 | PASS | AKHILA | 27.12.2024
|  | CR4_SC_001_TC_030 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_070 | PASS | AKHILA | 27.12.2024
|  | CR4_SC_001_TC_031 | PASS | AKHILA | 26.12.2024 |  |  | CR4_SC_002_TC_071 | PASS | AKHILA | 27.12.2024
|  | CR4_SC_001_TC_032 | PASS | AKHILA | 26.12.2024
|  | CR4_SC_001_TC_033 | PASS | AKHILA | 26.12.2024
|  | CR4_SC_001_TC_034 | PASS | AKHILA | 26.12.2024
|  | CR4_SC_001_TC_035 | PASS | AKHILA | 26.12.2024
|  | CR4_SC_001_TC_036 | PASS | AKHILA | 26.12.2024
|  | CR4_SC_001_TC_037 | PASS | AKHILA | 26.12.2024
|  | CR4_SC_001_TC_038 | PASS | AKHILA | 26.12.2024
|  | CR4_SC_001_TC_039 | PASS | AKHILA | 26.12.2024
|  | CR4_SC_001_TC_040 | PASS | AKHILA | 26.12.2024

## Daily Execution
2024-12-26 | Audit Report Phase 2 | Pass | Fail | InProgress | Blocked | Not Executed | Not Applicable | Total No of Test cases
|  | 44 | 1 | 0 | 0 | 60 | 0 | 105
2024-12-27 | Audit Report Phase 2 | Pass | Fail | InProgress | Blocked | Not Executed | Not Applicable | Total No of Test cases
|  | 74 | 1 | 0 | 4 | 26 | 0 | 105
2024-12-31 | Audit Report Phase 2 | Pass | Fail | InProgress | Blocked | Not Executed | Not Applicable | Total No of Test cases
|  | 103 | 2 | 0 | 9 | 0 | 0 | 114
ACCOUNT ACTIVATION DATE FIXED ON 06.01.2025
2024-01-06 | Audit Report Phase 2 | Pass | Fail | InProgress | Blocked | Not Executed | Not Applicable | Total No of Test cases
|  | 109 | 1 | 0 | 4 | 0 | 0 | 114