## Sheet1
ISSUE.NO | SCENARIO/ SC ID | TEST CASE/ TC ID | UAT STATUS | OBSERVATION | ITSM ID | STATUS | REMARKS
Audit Report_Issue_UAT_001 | Verification of Account amendments | Verify that the user is able to validate Account Activation Date in the audit report for the Changed / Modified Activation Date without any selection criteria. for Account Product: 1.At Call investment church 2.At Call Ministers and staff | FAIL | *Account Activation Date for the Changed / Modified Activation Date is not reflected in the audit report *Date of Change is in disorder way | ITSM-1855815 | CLOSED | Fixed on 06.01.2025 Test Passed
Audit Report_Issue_UAT_002 | Verification of Account amendments | Verify that the user is able to validate Account Activation Date in the audit report for the Changed / Modified Activation Date without any selection criteria. for Account Product: 1.At Call investment church 2.At Call Ministers and staff | FAIL | *Account and Customer amendements details filtering by Effective Date selection criteria is not working as expected. | ITSM-1861709 | OPEN
|  |  |  | The search options SmsPhonechange,TFN/ABN,Email UpdateCustomer under the selection criteria Activity not filtering the specific details but it listing all the other field amendements also. | ITSM-1861709 | OPEN